## Project Planner
[8 empty] | Week 1 |  |  |  |  | Week 2 | [6 empty] | Week 3 | [6 empty] | Week 4 | [6 empty] | Week 5 | [6 empty] | Week 6 | [6 empty] | Week 7 | [6 empty] | Week 8 | [6 empty] | Week 9 | [6 empty] | Week 10 | [6 empty] | Week 11 | [6 empty] | Week 12 | [6 empty] | Week 13 | [6 empty] | Week 14 | [6 empty] | Week 15 | [6 empty] | Week 16 | [6 empty] | Week 17
[40 empty] | Altium Component Library Review | [6 empty] | Schematic Review | [6 empty] | Layout Placement Review |  |  |  |  | Demo IDE Running |  | Layout Routing Review |  |  | Midterm |  |  |  | Final Design Review | [6 empty] | PCB released to fab | [8 empty] | PCB back for assembly | [5 empty] | Fall Break Week | [7 empty] | Assembly Complete | [14 empty] | Midterm 2 (Final) | [6 empty] | Project Demos
|  |  | Select a period to highlight at right. A legend describing the charting follows. |  |  |  |  | Period Highlight: |  | 34 |  |  | Plan Duration | [5 empty] | Actual Start | [5 empty] | Actual (beyond plan)
Project Planner | [18 empty] | % Complete | [5 empty] | % Complete (beyond plan)
[8 empty] | 2023-08-28 | 2023-08-29 | 2023-08-30 | September 1st | September 2nd | September 3rd | 2023-09-04 | 2023-09-05 | 2023-09-06 | 2023-09-07 | 2023-09-08 | 2023-09-09 | 2023-09-10 | 2023-09-11 | 2023-09-12 | 2023-09-13 | 2023-09-14 | 2023-09-15 | 2023-09-16 | 2023-09-17 | 2023-09-18 | 2023-09-19 | 2023-09-20 | 2023-09-21 | 2023-09-22 | 2023-09-23 | 2023-09-24 | 2023-09-25 | 2023-09-26 | 2023-09-27 | 2023-09-28 | 2023-09-29 |  | 2023-10-01 | 2023-10-02 | 2023-10-03 | 2023-10-04 | 2023-10-05 | 2023-10-06 |  | 2023-10-08 | 2023-10-09 | 2023-10-10 | 2023-10-11 | 2023-10-12 | 2023-10-13 |  | 2023-10-15 | 2023-10-16 | 2023-10-17 | 2023-10-18 |  | 2023-10-20 |  | 2023-10-22 | 2023-10-23 |  | 2023-10-25 | 2023-10-26 | 2023-10-27 |  | 2023-10-29 | 2023-10-30 | 2023-10-31 | 2023-11-01 | 2023-11-02 | 2023-11-03 |  | 2023-11-05 | 2023-11-06 | 2023-11-07 | 2023-11-08 | 2023-11-09 | 2023-11-10 | 2023-11-11 | 2023-11-12 |  | 2023-11-14 | 2023-11-15 | 2023-11-16 | 2023-11-17 | 2023-11-18 | [9 empty] | 2023-11-27 | 2023-11-28 | 2023-11-29 | 2023-11-30 | 2023-12-01 | 2023-12-02 | 2023-12-03 | 2023-12-04 | 2023-12-05 | 2023-12-06 | 2023-12-07 | 2023-12-08 | 2023-12-09 | 2023-12-10 |  | 2023-12-11 | 2023-12-12 | 2023-12-13 | Finals Week
ACTIVITY | LEAD | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | COMMENTS | PERIODS
[8 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99 | 100 | 101 | 102 | 103 | 104 | 105 | 106 | 107 | 108 | 109 | 110 | 111 | 112 | 113 | 114 | 115 | 116 | 117
Project Defined |  | 4 | 4 | 4 | 4 | 100%
Project Sensors Selection | Aneesh, Vaishnavi, Devang | 4 | 4 | 4 | 4 | 100%
Heart Rate and Oxygen level Sensors research and selection | Vaishnavi | 4 | 2 | 4 | 2 | 100%
Accerelometer: Sensor study and selection | Devang | 4 | 3 | 5 | 3 | 100%
GPS Module: Study and selection | Aneesh | 4 | 3 | 5 | 3 | 100%
Battery and Power Management Selection |  | 11 | 17 | 11 | 17
Peak average current calculation for the system | Devang | 18 | 1 | 18 | 1 | 100%
Search and finalize energy storage element | Aneesh | 13 | 1 | 13 | 1 | 100%
Search and finalize PMIC | Aneesh | 15 | 1 | 15 | 1 | 100%
Verify analysis of Use-case recharge time requirements | Vaishnavi | 26 | 1 | 26 | 1 | 100%
Verify analysis of sizing storage based on use case number of charge cycles | Aneesh | 26 | 1 | 26 | 1 | 100%
MAX30102 Power consumption analysis | Vaishnavi | 11 | 1 | 11 | 1 | 100%
LIS3DH Power consumption analysis | Devang | 12 | 1 | 12 | 1 | 100%
SAM-M8Q Power consumption analysis | Aneesh | 15 | 1 | 15 | 1 | 100%
Verify C-Rate and Discharge Rate for selcted Battery | Aneesh | 27 | 1 | 27 | 1 | 100%
Design Phase |  | 13 | 16 | 13 | 16
Initial sensor working modes design | Aneesh, Vaishnavi, Devang | 13 | 2 | 14 | 2 | 100%
Use case model & energy storage element math | Aneesh, Vaishnavi, Devang | 14 | 1 | 15 | 1 | 100%
Dataflow diagram | Devang | 17 | 1 | 22 | 1 | 100%
Update sensor interface selection and it's reasoning | Vaishnavi | 20 | 1 | 23 | 1 | 100%
Determine max time taken by sensors to find EM requirements | Devang | 20 | 1 | 23 | 1 | 100%
Add energy mode breakdown and sensor state analysis. | Devang | 20 | 1 | 23 | 1 | 100%
Find worst case communication bus time: Accelerometer | Devang | 27 | 1 | 28 | 1 | 100%
Find worst case communication bus time: HR and SPO2 | Vaishnavi | 27 | 1 | 28 | 1 | 100%
Find worst case communication bus time: GPS Module | Devang | 27 | 1 | 28 | 1 | 100%
Energy Harvesting and Calculation: Solar Panels | Vaishnavi | 29 | 1 | 29 | 1 | 100%
Check Solar Panel Specifications
Spice Analysis of Power Supplies
Altium Tasks |  | 25 | 4 | 27 | 3 | 100%
Altium Library: GPS Module | Aneesh | 27 | 3 | 27 | 3 | 100%
Altium Library: HR and SPO2 | Aneesh | 27 | 3 | 27 | 3 | 100%
Altium Library: PMIC | Aneesh | 27 | 3 | 27 | 3 | 100%
Altium Library: EFR32BG13 | Vaishnavi | 27 | 3 | 27 | 3 | 100%
Altium Library: LIS3DH | Devang | 27 | 3 | 27 | 3 | 100%
Altium Library: Miscellaneous Parts | Aneesh | 27 | 3 | 27 | 3 | 100%
Schematic Development |  | 33 | 6 | 0 | 0 | 0%
Schematic Review |  | 37 | 1
Layout Development |  | 40 | 6 | 0 | 0 | 0%
Layout Review |  | 47 | 1 | 0 | 0 | 0%
Layout Routing |  | 47 | 6
Sensor Interfacing and Testing |  | 34 | 17
Sensor Interfacing: GPS Module | Aneesh | 34 | 17 |  |  | 0%
Sensor Interfacing: Heart Rate and SpO2 Module | Vaishnavi | 34 | 17 |  |  | 0%
Sensor Interfacing: Accelerometer | Devang | 34 | 17 |  |  | 0%
Verification of sensors: GPS Module | Aneesh | 34 | 17 |  |  | 0%
Verification of sensors: Heart Rate and SpO2 Module | Vaishnavi | 34 | 17 |  |  | 0%
Verification of sensors: Accelerometer | Devang | 34 | 17 |  |  | 0%
|  | 0 |  |  |  | 0%
|  | 0 |  |  |  | 0%
Course Demo |  | 52 | 1
Premilinary Software Demo |  | 52 | 1
Firmware Development |  | 55 | 36 |  |  | 0%
Application Development |  | 55 | 45 |  |  | 0%
PCB Assembly |  | 77 | 14 |  |  | 0%
Bringup and Verification |  | 92 | 13 |  |  | 0%